## Lip Balm
Product | • Lip Lightening Balm |  |  | Duration | 101
Tasks | Tasks | Tasks | L1 | POC (CAP) | Start Date | End Date | Current Status | Completion Date | TAT | Delay
Task 1 | Project Initiation | Not applicable | 1 | Aman P | 2024-04-12 | 2024-04-13 | Done | 2024-04-15 | 4 | 2
Task 2 | Marketing and R&D Research | Task 1 | 8 | Swarnita | 2024-04-13 | 2024-04-21 | Done | 2024-04-16 | 4 | 0
Task 3 | Benchmarking | Task 2 | 2 | Swarnita | 2024-04-21 | 2024-04-23 | Done | 2024-04-23 | 3 | 0
Task 4 | Brainstorming Call & Ideation approval | Task 2 & 3 | 2 | Aman P | 2024-04-23 | 2024-04-25 | Done | 2024-04-24 | 2 | 0
Task 5 | Product Development Brief (PDB) | Task 2 & 3 | 2 | Swarnita | 2024-04-25 | 2024-04-27 | Done | 2024-04-29 | 5 | 2
Task 6 | Kick-off Meeting | Task 5 | 1 | Swarnita | 2024-04-27 | 2024-04-28 | Done | 2024-04-28 | 2 | 0
Task 7 | Fragrance Sampling & Evaluation | Task 6 | 2 | Khushbu | 2024-04-28 | 2024-04-30 | Yet to start
Task 8 | RM Sourcing for Prototype | Task 6 | 5 | Khushbu | 2024-04-28 | 2024-05-03 | Yet to start
Task 9 | Packaging Sampling & Color Development | Task 6 | 6 | Sonu | 2024-04-28 | 2024-05-04 | Yet to start
Task 10 | Prototype Development (T1) | Task 6, 7 & 8 | 5 | Khushbu | 2024-05-04 | 2024-05-09 | Yet to start
Task 11 | Internal Studies (T1) | Task 10 | 3 | Khushbu | 2024-05-09 | 2024-05-12 | Yet to start
Task 12 | Prototype Reformulation (T2) | Task 11 | 4 | Khushbu | 2024-05-12 | 2024-05-16 | Yet to start
Task 13 | Internal Studies (T2) | Task 12 | 3 | Khushbu | 2024-05-16 | 2024-05-19 | Yet to start
Task 14 | Consumer Recruitment | Task 13 | 14 | Ruchi | 2024-05-19 | 2024-06-02 | Yet to start
Task 15 | Product & Packaging Stability Phase-1 | Task 13 | 11 | Khushbu/ Sonu | 2024-05-19 | 2024-05-30 | Yet to start
Task 16 | Product & Packaging Stability Phase-2 | Task 15 | 10 | Khushbu/ Sonu | 2024-05-30 | 2024-06-09 | Yet to start
Task 17 | 3 Months Accelerated Stability Study | Task 13 | 90 | Khushbu | 2024-05-19 | 2024-08-17 | Yet to start
Task 19 | Final formulation approval | Task 15 | 1 | Vimal Sir/ Rohit | 2024-05-30 | 2024-05-31 | Yet to start
Task 20 | Lab Certification | Task 19 | 15 | Khushbu | 2024-05-31 | 2024-06-15 | Yet to start
Task 21 | Draft Label / Tube Content | Task 19 | 2 | Swarnita | 2024-05-31 | 2024-06-02 | Yet to start
Task 22 | Concept Deck - Completion | Task 21 | 2 | Swarnita | 2024-06-02 | 2024-06-04 | Yet to start
Task 23 | Content Creation (CC) Document | Task 22 | 1 | Rashi | 2024-06-04 | 2024-06-05 | Yet to start
Task 24 | Social Media pre-launch build up | Task 23 | - | Rashi/Georgia | - | - | Yet to start
Task 25 | Content Work for Packaging | Task 23 | 2 | Swarnita | 2024-06-05 | 2024-06-07 | Yet to start
Task 26 | Designing Work for Packaging | Task 25 | 3 | Shaan | 2024-06-07 | 2024-06-10 | Yet to start
Task 27 | Product Approval Form (PAF) preparation | Task 16 & 19 | 5 | AP | 2024-06-10 | 2024-06-15 | Yet to start
Task 28 | Claims Support Dosier (CSD) | Task 16 & 19 | 5 | AP | 2024-06-15 | 2024-06-20 | Yet to start
Task 29 | Raw Material PO | Task 15 | 1 | Ranjan | 2024-05-30 | 2024-05-31 | Yet to start
Task 30 | Packaging Material PO Primary | Task 15 | 1 | Sonu | 2024-05-30 | 2024-05-31 | Yet to start
Task 31 | Packaging Material PO Secondary | Task 26 | 1 | Sonu | 2024-06-10 | 2024-06-11 | Yet to start
Task 32 | Costing Master Update (CMU) | Task 29, 30 & 31 | 1 | Swarnita | 2024-06-11 | 2024-06-12 | Yet to start
Task 33 | Raw Material receiving | Task 29 | 20 | Ranjan | 2024-05-31 | 2024-06-20 | Yet to start
Task 34 | Packaging Material Primary receiving | Task 30 | 30 | Sonu | 2024-05-31 | 2024-06-30 | Yet to start
Task 35 | Packaging Material Secondary receiving | Task 31 | 20 | Sonu | 2024-06-11 | 2024-07-01 | Yet to start
Task 36 | Finished Goods | Task 33, 34 & 35 | 3 | Ranjan / Nekunj | 2024-07-01 | 2024-07-04 | Yet to start
Task 37 | Accerlerated and Long term stability for FG - 3 Months - 12 Months - 24 Months | Task 36 | 90 | Khushbu | 2024-07-04 | 2024-10-02 | Yet to start
Task 38 | Photoshoot | Task 36 | 2 | Rashi/Animesh | 2024-07-04 | 2024-07-06 | Yet to start
Task 39 | Launch Assets Preparation | Task 38 | 7 | Shaan | 2024-07-06 | 2024-07-13 | Yet to start
Task 40 | Launch Asset Approval | Task 39 | 3 | Swarnita | 2024-07-13 | 2024-07-16 | Yet to start
Task 41 | Updating links in New Launch Requirement sheet | Task 40 | 3 | - | 2024-07-16 | 2024-07-19 | Yet to start
Task 42 | Innovist Website Launch | Task 41 | 2 | Muskan | 2024-07-19 | 2024-07-21 | Yet to start
Task 43 | Amazon & Flipkart | Task 41 | 2 | Aditya/ Raghu | 2024-07-19 | 2024-07-21 | Yet to start
Task 44 | Other marketplaces | Task 41 | 1 | Zaid/Yukta/Lokesh | 2024-07-19 | 2024-07-20 | Yet to start
Task 45 | Post launch product feedback analysis | Task 42,43 & 44 | 100 | Ruchi | 2024-07-20 | 2024-10-28 | Yet to start
Task 46 | Net Promoter Score (NPS) Calculation | Task 45 | 2 | Ruchi | 2024-10-28 | 2024-10-30 | Yet to start
Formulas:
End Date = [Start Date]+[L1]
Start Date = [End Date, row above]

## Gannt View 1
Tasks | Name | Start Date | End Date | Current Status | Completion Date | TAT | Delay
Task 1 | Project Initiation | 2024-04-12 | 2024-04-13 | Done | 2024-04-15 | 4 | 2
Task 2 | Marketing and R&D Research | 2024-04-13 | 2024-04-21 | Done | 2024-04-16 | 4 | 0
Task 3 | Benchmarking | 2024-04-21 | 2024-04-23 | Done | 2024-04-23 | 3 | 0
Task 4 | Brainstorming Call & Ideation approval | 2024-04-23 | 2024-04-25 | Done | 2024-04-24 | 2 | 0
Task 5 | Product Development Brief (PDB) | 2024-04-25 | 2024-04-27 | Done | 2024-04-29 | 5 | 2
Task 6 | Kick-off Meeting | 2024-04-27 | 2024-04-28 | Done | 2024-04-28 | 2 | 0
Task 7 | Fragrance Sampling & Evaluation | 2024-04-28 | 2024-04-30 | Yet to start
Task 8 | RM Sourcing for Prototype | 2024-04-28 | 2024-05-03 | Yet to start
Task 9 | Packaging Sampling & Color Development | 2024-04-28 | 2024-05-04 | Yet to start
Task 10 | Prototype Development (T1) | 2024-05-04 | 2024-05-09 | Yet to start
Task 11 | Internal Studies (T1) | 2024-05-09 | 2024-05-12 | Yet to start
Task 12 | Prototype Reformulation (T2) | 2024-05-12 | 2024-05-16 | Yet to start
Task 13 | Internal Studies (T2) | 2024-05-16 | 2024-05-19 | Yet to start
Task 14 | Consumer Recruitment | 2024-05-19 | 2024-06-02 | Yet to start
Task 15 | Product & Packaging Stability Phase-1 | 2024-05-19 | 2024-05-30 | Yet to start
Task 16 | Product & Packaging Stability Phase-2 | 2024-05-30 | 2024-06-09 | Yet to start
Task 17 | 3 Months Accelerated Stability Study | 2024-05-19 | 2024-08-17 | Yet to start
Task 19 | Final formulation approval | 2024-05-30 | 2024-05-31 | Yet to start
Task 20 | Lab Certification | 2024-05-31 | 2024-06-15 | Yet to start
Task 21 | Draft Label / Tube Content | 2024-05-31 | 2024-06-02 | Yet to start
Task 22 | Concept Deck - Completion | 2024-06-02 | 2024-06-04 | Yet to start
Task 23 | Content Creation (CC) Document | 2024-06-04 | 2024-06-05 | Yet to start
Task 24 | Social Media pre-launch build up | - | - | Yet to start
Task 25 | Content Work for Packaging | 2024-06-05 | 2024-06-07 | Yet to start
Task 26 | Designing Work for Packaging | 2024-06-07 | 2024-06-10 | Yet to start
Task 27 | Product Approval Form (PAF) preparation | 2024-06-10 | 2024-06-15 | Yet to start
Task 28 | Claims Support Dosier (CSD) | 2024-06-15 | 2024-06-20 | Yet to start
Task 29 | Raw Material PO | 2024-05-30 | 2024-05-31 | Yet to start
Task 30 | Packaging Material PO Primary | 2024-05-30 | 2024-05-31 | Yet to start
Task 31 | Packaging Material PO Secondary | 2024-06-10 | 2024-06-11 | Yet to start
Task 32 | Costing Master Update (CMU) | 2024-06-11 | 2024-06-12 | Yet to start
Task 33 | Raw Material receiving | 2024-05-31 | 2024-06-20 | Yet to start
Task 34 | Packaging Material Primary receiving | 2024-05-31 | 2024-06-30 | Yet to start
Task 35 | Packaging Material Secondary receiving | 2024-06-11 | 2024-07-01 | Yet to start
Task 36 | Finished Goods | 2024-07-01 | 2024-07-04 | Yet to start
Task 37 | Accerlerated and Long term stability for FG - 3 Months - 12 Months - 24 Months | 2024-07-04 | 2024-10-02 | Yet to start
Task 38 | Photoshoot | 2024-07-04 | 2024-07-06 | Yet to start
Task 39 | Launch Assets Preparation | 2024-07-06 | 2024-07-13 | Yet to start
Task 40 | Launch Asset Approval | 2024-07-13 | 2024-07-16 | Yet to start
Task 41 | Updating links in New Launch Requirement sheet | 2024-07-16 | 2024-07-19 | Yet to start
Task 42 | Innovist Website Launch | 2024-07-19 | 2024-07-21 | Yet to start
Task 43 | Amazon & Flipkart | 2024-07-19 | 2024-07-21 | Yet to start
Task 44 | Other marketplaces | 2024-07-19 | 2024-07-20 | Yet to start
Task 45 | Post launch product feedback analysis | 2024-07-20 | 2024-10-28 | Yet to start
Task 46 | Net Promoter Score (NPS) Calculation | 2024-10-28 | 2024-10-30 | Yet to start

## Gaant View 2
Tasks | Name | Start Date | End Date | Current Status | Completion Date | TAT | Delay
Task 1 | Project Initiation | 2024-04-12 | 2024-04-13 | Done | 2024-04-15 | 4 | 2
Task 2 | Marketing and R&D Research | 2024-04-13 | 2024-04-21 | Done | 2024-04-16 | 4 | 0
Task 3 | Benchmarking | 2024-04-21 | 2024-04-23 | Done | 2024-04-23 | 3 | 0
Task 4 | Brainstorming Call & Ideation approval | 2024-04-23 | 2024-04-25 | Done | 2024-04-24 | 2 | 0
Task 5 | Product Development Brief (PDB) | 2024-04-25 | 2024-04-27 | Done | 2024-04-29 | 5 | 2
Task 6 | Kick-off Meeting | 2024-04-27 | 2024-04-28 | Done | 2024-04-28 | 2 | 0
Task 7 | Fragrance Sampling & Evaluation | 2024-04-28 | 2024-04-30 | Yet to start
Task 8 | RM Sourcing for Prototype | 2024-04-28 | 2024-05-03 | Yet to start
Task 9 | Packaging Sampling & Color Development | 2024-04-28 | 2024-05-04 | Yet to start
Task 10 | Prototype Development (T1) | 2024-05-04 | 2024-05-09 | Yet to start
Task 11 | Internal Studies (T1) | 2024-05-09 | 2024-05-12 | Yet to start
Task 12 | Prototype Reformulation (T2) | 2024-05-12 | 2024-05-16 | Yet to start
Task 13 | Internal Studies (T2) | 2024-05-16 | 2024-05-19 | Yet to start
Task 14 | Consumer Recruitment | 2024-05-19 | 2024-06-02 | Yet to start
Task 15 | Product & Packaging Stability Phase-1 | 2024-05-19 | 2024-05-30 | Yet to start
Task 16 | Product & Packaging Stability Phase-2 | 2024-05-30 | 2024-06-09 | Yet to start
Task 17 | 3 Months Accelerated Stability Study | 2024-05-19 | 2024-08-17 | Yet to start
Task 19 | Final formulation approval | 2024-05-30 | 2024-05-31 | Yet to start
Task 20 | Lab Certification | 2024-05-31 | 2024-06-15 | Yet to start
Task 21 | Draft Label / Tube Content | 2024-05-31 | 2024-06-02 | Yet to start
Task 22 | Concept Deck - Completion | 2024-06-02 | 2024-06-04 | Yet to start
Task 23 | Content Creation (CC) Document | 2024-06-04 | 2024-06-05 | Yet to start
Task 24 | Social Media pre-launch build up | - | - | Yet to start
Task 25 | Content Work for Packaging | 2024-06-05 | 2024-06-07 | Yet to start
Task 26 | Designing Work for Packaging | 2024-06-07 | 2024-06-10 | Yet to start
Task 27 | Product Approval Form (PAF) preparation | 2024-06-10 | 2024-06-15 | Yet to start
Task 28 | Claims Support Dosier (CSD) | 2024-06-15 | 2024-06-20 | Yet to start
Task 29 | Raw Material PO | 2024-05-30 | 2024-05-31 | Yet to start
Task 30 | Packaging Material PO Primary | 2024-05-30 | 2024-05-31 | Yet to start
Task 31 | Packaging Material PO Secondary | 2024-06-10 | 2024-06-11 | Yet to start
Task 32 | Costing Master Update (CMU) | 2024-06-11 | 2024-06-12 | Yet to start
Task 33 | Raw Material receiving | 2024-05-31 | 2024-06-20 | Yet to start
Task 34 | Packaging Material Primary receiving | 2024-05-31 | 2024-06-30 | Yet to start
Task 35 | Packaging Material Secondary receiving | 2024-06-11 | 2024-07-01 | Yet to start
Task 36 | Finished Goods | 2024-07-01 | 2024-07-04 | Yet to start
Task 37 | Accerlerated and Long term stability for FG - 3 Months - 12 Months - 24 Months | 2024-07-04 | 2024-10-02 | Yet to start
Task 38 | Photoshoot | 2024-07-04 | 2024-07-06 | Yet to start
Task 39 | Launch Assets Preparation | 2024-07-06 | 2024-07-13 | Yet to start
Task 40 | Launch Asset Approval | 2024-07-13 | 2024-07-16 | Yet to start
Task 41 | Updating links in New Launch Requirement sheet | 2024-07-16 | 2024-07-19 | Yet to start
Task 42 | Innovist Website Launch | 2024-07-19 | 2024-07-21 | Yet to start
Task 43 | Amazon & Flipkart | 2024-07-19 | 2024-07-21 | Yet to start
Task 44 | Other marketplaces | 2024-07-19 | 2024-07-20 | Yet to start
Task 45 | Post launch product feedback analysis | 2024-07-20 | 2024-10-28 | Yet to start
Task 46 | Net Promoter Score (NPS) Calculation | 2024-10-28 | 2024-10-30 | Yet to start

## Gaant View 3
Name | Start Date | End Date | Current Status | time axis 2024-04-12 to 2024-10-31
Project Initiation | 2024-04-12 | 2024-04-13 | Done | bar: 2024-04-12 to 2024-04-13
Marketing and R&D Research | 2024-04-13 | 2024-04-21 | Done | bar: 2024-04-13 to 2024-04-21
Benchmarking | 2024-04-21 | 2024-04-23 | Done | bar: 2024-04-21 to 2024-04-23
Brainstorming Call & Ideation approval | 2024-04-23 | 2024-04-25 | Done | bar: 2024-04-23 to 2024-04-25
Product Development Brief (PDB) | 2024-04-25 | 2024-04-27 | Done | bar: 2024-04-25 to 2024-04-27
Kick-off Meeting | 2024-04-27 | 2024-04-28 | Done | bar: 2024-04-27 to 2024-04-28
Fragrance Sampling & Evaluation | 2024-04-28 | 2024-04-30 | Yet to start | bar: 2024-04-28 to 2024-04-30
RM Sourcing for Prototype | 2024-04-28 | 2024-05-03 | Yet to start | bar: 2024-04-28 to 2024-05-03
Packaging Sampling & Color Development | 2024-04-28 | 2024-05-04 | Yet to start | bar: 2024-04-28 to 2024-05-04
Prototype Development (T1) | 2024-05-04 | 2024-05-09 | Yet to start | bar: 2024-05-04 to 2024-05-09
Internal Studies (T1) | 2024-05-09 | 2024-05-12 | Yet to start | bar: 2024-05-09 to 2024-05-12
Prototype Reformulation (T2) | 2024-05-12 | 2024-05-16 | Yet to start | bar: 2024-05-12 to 2024-05-16
Internal Studies (T2) | 2024-05-16 | 2024-05-19 | Yet to start | bar: 2024-05-16 to 2024-05-19
Consumer Recruitment | 2024-05-19 | 2024-06-02 | Yet to start | bar: 2024-05-19 to 2024-06-02
Product & Packaging Stability Phase-1 | 2024-05-19 | 2024-05-30 | Yet to start | bar: 2024-05-19 to 2024-05-30
Product & Packaging Stability Phase-2 | 2024-05-30 | 2024-06-09 | Yet to start | bar: 2024-05-30 to 2024-06-09
3 Months Accelerated Stability Study | 2024-05-19 | 2024-08-17 | Yet to start | bar: 2024-05-19 to 2024-08-17
Final formulation approval | 2024-05-30 | 2024-05-31 | Yet to start | bar: 2024-05-30 to 2024-05-31
Lab Certification | 2024-05-31 | 2024-06-15 | Yet to start | bar: 2024-05-31 to 2024-06-15
Draft Label / Tube Content | 2024-05-31 | 2024-06-02 | Yet to start | bar: 2024-05-31 to 2024-06-02
Concept Deck - Completion | 2024-06-02 | 2024-06-04 | Yet to start | bar: 2024-06-02 to 2024-06-04
Content Creation (CC) Document | 2024-06-04 | 2024-06-05 | Yet to start | bar: 2024-06-04 to 2024-06-05
Social Media pre-launch build up | - | - | Yet to start
Content Work for Packaging | 2024-06-05 | 2024-06-07 | Yet to start | bar: 2024-06-05 to 2024-06-07
Designing Work for Packaging | 2024-06-07 | 2024-06-10 | Yet to start | bar: 2024-06-07 to 2024-06-10
Product Approval Form (PAF) preparation | 2024-06-10 | 2024-06-15 | Yet to start | bar: 2024-06-10 to 2024-06-15
Claims Support Dosier (CSD) | 2024-06-15 | 2024-06-20 | Yet to start | bar: 2024-06-15 to 2024-06-20
Raw Material PO | 2024-05-30 | 2024-05-31 | Yet to start | bar: 2024-05-30 to 2024-05-31
Packaging Material PO Primary | 2024-05-30 | 2024-05-31 | Yet to start | bar: 2024-05-30 to 2024-05-31
Packaging Material PO Secondary | 2024-06-10 | 2024-06-11 | Yet to start | bar: 2024-06-10 to 2024-06-11
Costing Master Update (CMU) | 2024-06-11 | 2024-06-12 | Yet to start | bar: 2024-06-11 to 2024-06-12
Raw Material receiving | 2024-05-31 | 2024-06-20 | Yet to start | bar: 2024-05-31 to 2024-06-20
Packaging Material Primary receiving | 2024-05-31 | 2024-06-30 | Yet to start | bar: 2024-05-31 to 2024-06-30
Packaging Material Secondary receiving | 2024-06-11 | 2024-07-01 | Yet to start | bar: 2024-06-11 to 2024-07-01
Finished Goods | 2024-07-01 | 2024-07-04 | Yet to start | bar: 2024-07-01 to 2024-07-04
Accerlerated and Long term stability for FG - 3 Months - 12 Months - 24 Months | 2024-07-04 | 2024-10-02 | Yet to start | bar: 2024-07-04 to 2024-10-02
Photoshoot | 2024-07-04 | 2024-07-06 | Yet to start | bar: 2024-07-04 to 2024-07-06
Launch Assets Preparation | 2024-07-06 | 2024-07-13 | Yet to start | bar: 2024-07-06 to 2024-07-13
Launch Asset Approval | 2024-07-13 | 2024-07-16 | Yet to start | bar: 2024-07-13 to 2024-07-16
Updating links in New Launch Requirement sheet | 2024-07-16 | 2024-07-19 | Yet to start | bar: 2024-07-16 to 2024-07-19
Innovist Website Launch | 2024-07-19 | 2024-07-21 | Yet to start | bar: 2024-07-19 to 2024-07-21
Amazon & Flipkart | 2024-07-19 | 2024-07-21 | Yet to start | bar: 2024-07-19 to 2024-07-21
Other marketplaces | 2024-07-19 | 2024-07-20 | Yet to start | bar: 2024-07-19 to 2024-07-20
Post launch product feedback analysis | 2024-07-20 | 2024-10-28 | Yet to start | bar: 2024-07-20 to 2024-10-28
Net Promoter Score (NPS) Calculation | 2024-10-28 | 2024-10-30 | Yet to start | bar: 2024-10-28 to 2024-10-30

## Gaant View 4
Name | Start Date | End Date | Completion Time | Current Status | time axis 2024-04-12 to 2024-10-30
Project Initiation | 2024-04-12 | 2024-04-13 | 2024-04-15 | Done | bar: 2024-04-12 to 2024-04-15
Marketing and R&D Research | 2024-04-13 | 2024-04-21 | 2024-04-16 | Done | bar: 2024-04-13 to 2024-04-16
Benchmarking | 2024-04-21 | 2024-04-23 | 2024-04-23 | Done | bar: 2024-04-21 to 2024-04-23
Brainstorming Call & Ideation approval | 2024-04-23 | 2024-04-25 | 2024-04-24 | Done | bar: 2024-04-23 to 2024-04-24
Product Development Brief (PDB) | 2024-04-25 | 2024-04-27 | 2024-04-29 | Done | bar: 2024-04-25 to 2024-04-29
Kick-off Meeting | 2024-04-27 | 2024-04-28 | 2024-04-28 | Done | bar: 2024-04-27 to 2024-04-28
Fragrance Sampling & Evaluation | 2024-04-28 | 2024-04-30 |  | Yet to start
RM Sourcing for Prototype | 2024-04-28 | 2024-05-03 |  | Yet to start
Packaging Sampling & Color Development | 2024-04-28 | 2024-05-04 |  | Yet to start
Prototype Development (T1) | 2024-05-04 | 2024-05-09 |  | Yet to start
Internal Studies (T1) | 2024-05-09 | 2024-05-12 |  | Yet to start
Prototype Reformulation (T2) | 2024-05-12 | 2024-05-16 |  | Yet to start
Internal Studies (T2) | 2024-05-16 | 2024-05-19 |  | Yet to start
Consumer Recruitment | 2024-05-19 | 2024-06-02 |  | Yet to start
Product & Packaging Stability Phase-1 | 2024-05-19 | 2024-05-30 |  | Yet to start
Product & Packaging Stability Phase-2 | 2024-05-30 | 2024-06-09 |  | Yet to start
3 Months Accelerated Stability Study | 2024-05-19 | 2024-08-17 |  | Yet to start
Final formulation approval | 2024-05-30 | 2024-05-31 |  | Yet to start
Lab Certification | 2024-05-31 | 2024-06-15 |  | Yet to start
Draft Label / Tube Content | 2024-05-31 | 2024-06-02 |  | Yet to start
Concept Deck - Completion | 2024-06-02 | 2024-06-04 |  | Yet to start
Content Creation (CC) Document | 2024-06-04 | 2024-06-05 |  | Yet to start
Social Media pre-launch build up | - | - |  | Yet to start
Content Work for Packaging | 2024-06-05 | 2024-06-07 |  | Yet to start
Designing Work for Packaging | 2024-06-07 | 2024-06-10 |  | Yet to start
Product Approval Form (PAF) preparation | 2024-06-10 | 2024-06-15 |  | Yet to start
Claims Support Dosier (CSD) | 2024-06-15 | 2024-06-20 |  | Yet to start
Raw Material PO | 2024-05-30 | 2024-05-31 |  | Yet to start
Packaging Material PO Primary | 2024-05-30 | 2024-05-31 |  | Yet to start
Packaging Material PO Secondary | 2024-06-10 | 2024-06-11 |  | Yet to start
Costing Master Update (CMU) | 2024-06-11 | 2024-06-12 |  | Yet to start
Raw Material receiving | 2024-05-31 | 2024-06-20 |  | Yet to start
Packaging Material Primary receiving | 2024-05-31 | 2024-06-30 |  | Yet to start
Packaging Material Secondary receiving | 2024-06-11 | 2024-07-01 |  | Yet to start
Finished Goods | 2024-07-01 | 2024-07-04 |  | Yet to start
Accerlerated and Long term stability for FG - 3 Months - 12 Months - 24 Months | 2024-07-04 | 2024-10-02 |  | Yet to start
Photoshoot | 2024-07-04 | 2024-07-06 |  | Yet to start
Launch Assets Preparation | 2024-07-06 | 2024-07-13 |  | Yet to start
Launch Asset Approval | 2024-07-13 | 2024-07-16 |  | Yet to start
Updating links in New Launch Requirement sheet | 2024-07-16 | 2024-07-19 |  | Yet to start
Innovist Website Launch | 2024-07-19 | 2024-07-21 |  | Yet to start
Amazon & Flipkart | 2024-07-19 | 2024-07-21 |  | Yet to start
Other marketplaces | 2024-07-19 | 2024-07-20 |  | Yet to start
Post launch product feedback analysis | 2024-07-20 | 2024-10-28 |  | Yet to start
Net Promoter Score (NPS) Calculation | 2024-10-28 | 2024-10-30 |  | Yet to start

## Project_Master_Sheet
Project_ID | Project_Name | Product_Name | Start_Date | End_Date | Total_Tasks | Completed_Tasks | Completion_PCT | Delayed_Tasks | POC | Risk_Status | Last_Updated
PRJ-001 | Project A | Lip Balm | 2024-05-15 | 2024-11-12 | 35 | 12 | 34% | 2 | Aman P | 0 | 2024-05-28 14:30
PRJ-002 | Project B | Hair Serum | 2024-06-01 | 2024-11-25 | 42 | 38 | 90% | 0 | Swarnita | Low | 2024-10-16 14:30
PRJ-003 | Project C | Face Cream | 2024-04-10 | 2024-10-05 | 28 | 5 | 18% | 4 | Khushbu | High | 2024-07-07 14:30
PRJ-004 | Project D | Sunscreen | 2024-05-20 | 2024-08-15 | 31 | 22 | 71% | 1 | Sonu | Medium | 2024-06-28 14:30
PRJ-005 | Project E | Shampoo | 2024-03-05 | 2024-09-10 | 45 | 40 | 89% | 0 | Ruchi | Low | 2024-08-28 14:30
PRJ-006 | Project F | Lip Balm | 2024-06-10 | 2024-12-01 | 38 | 15 | 39% | 3 | Aman P | Medium | 2024-09-28 14:30
PRJ-007 | Project G | Hair Serum | 2024-05-01 | 2024-08-20 | 27 | 8 | 30% | 2 | Swarnita | Medium | 2024-08-29 14:30
PRJ-008 | Project H | Face Cream | 2024-04-25 | 2024-07-30 | 33 | 28 | 85% | 0 | Khushbu | Low | 2024-07-02 14:30
PRJ-009 | Project I | Sunscreen | 2024-06-05 | 2024-09-18 | 29 | 10 | 34% | 1 | Sonu | Medium | 2024-09-12 14:30
PRJ-010 | Project J | Shampoo | 2024-03-15 | 2024-06-30 | 40 | 36 | 90% | 0 | Ruchi | Low | 2024-06-28 14:30
PRJ-011 | Project K | Lip Balm | 2024-05-28 | 2024-11-15 | 36 | 12 | 33% | 3 | Aman P | Medium | 2024-10-12 14:30
PRJ-012 | Project L | Hair Serum | 2024-04-10 | 2024-07-22 | 26 | 20 | 77% | 1 | Swarnita | Medium | 2024-06-12 14:30
PRJ-013 | Project M | Face Cream | 2024-06-01 | 2024-08-10 | 32 | 25 | 78% | 0 | Khushbu | Low | 2024-08-08 14:30
PRJ-014 | Project N | Sunscreen | 2024-05-12 | 2024-07-28 | 30 | 18 | 60% | 2 | Sonu | Medium | 2024-07-20 14:30
PRJ-015 | Project O | Shampoo | 2024-03-20 | 2024-05-30 | 22 | 20 | 91% | 0 | Ruchi | Low | 2024-05-26 14:30
PRJ-016 | Project P | Lip Balm | 2024-06-15 | 2024-12-20 | 41 | 14 | 34% | 4 | Aman P | Medium | 2024-12-12 14:30
PRJ-017 | Project Q | Hair Serum | 2024-05-05 | 2024-08-08 | 28 | 21 | 75% | 1 | Swarnita | Medium | 2024-06-28 14:30
PRJ-018 | Project R | Face Cream | 2024-04-18 | 2024-06-25 | 24 | 17 | 71% | 0 | Khushbu | Medium | 2024-06-22 14:30
PRJ-019 | Project S | Sunscreen | 2024-06-08 | 2024-09-02 | 35 | 26 | 74% | 1 | Sonu | Medium | 2024-05-28 14:30
PRJ-020 | Project T | Shampoo | 2024-03-10 | 2024-05-20 | 19 | 17 | 89% | 0 | Ruchi | Low | 2024-05-28 14:30

## KPI & Pivot Table
KPI, Pivot Table, Filter & Slicer
Total Projects |  | 20 | Risk_Status | (All) | Risk_Status | (Multiple Items)
Avg Completion % |  | 63.1% | POC | Average of Completed_Tasks | Product | Sum of Total_Tasks
|  |  | Swarnita | 21.75 | Face Cream | 93
Delayed Projects |  | 12 | Sonu | 19 | Hair Serum | 42
|  |  | Ruchi | 28.25 | Shampoo | 126
High Risk Projects |  | 1 | Khushbu | 18.75 | Grand Total | 261
|  |  | Aman P | 13.25
|  |  | Grand Total | 2020%
Risk_Status | (All)
POC | (All) |  |  |  | Product_Name | (All)
Projects | Average of Completion_PCT |  | Risk Status | Count of Project_Name | Risk Status | Percentage of Completion_PCT
Project A | 34% |  | High | 1 | 2024
Project B | 90% |  | Low | 7 | May | 90%
Project C | 18% |  | Medium | 12 | Jun | 80.5%
Project D | 71% |  | Grand Total | 20 | Jul | 74%
Project E | 89% |  |  |  | Aug | 63.5%
Project F | 39% |  |  |  | Sep | 65.67% | Risk Status | Count of Delayed_Tasks
Project G | 30% |  |  |  | Oct | 18% | Face Cream | 4
Project H | 85% |  |  |  | Nov | 52.33% | Apr | 3
Project I | 34% |  | POC | Sum of Delayed_Days | Dec | 36.5% | Jun | 1
Project J | 90% |  | Aman P | 12 | Grand Total | 0.631 | Hair Serum | 4
Project K | 33% |  | Khushbu | 4 |  |  | Apr | 1
Project L | 77% |  | Ruchi | 0 |  |  | May | 2
Project M | 78% |  | Sonu | 5 |  |  | Jun | 1
Project N | 60% |  | Swarnita | 4 |  |  | Lip Balm | 4
Project O | 91% |  | Grand Total | 25 |  |  | May | 2
Project P | 34% | [5 empty] | Jun | 2
Project Q | 75% | [5 empty] | Shampoo | 4
Project R | 71% | [5 empty] | Mar | 4
Project S | 74% | [5 empty] | Sunscreen | 4
Project T | 89% | [5 empty] | May | 2
Grand Total | 63.1% | [5 empty] | Jun | 2
[7 empty] | Grand Total | 20
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DashBoard
Project Dashboard
Total Projects
Avg Completion%
No. Delayed Projects
High Rish Project
20
63%
12
1
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.